## Sheet1
Task Name: | Agent-Names | Task Description | Status
Unit Testing Using Qt, of System 1 code | Eric, Ryan | Created test case to verify functionality of the original system | Completed
Questions for Customer | Ryan, Haris, Leroi, Novia, Stephan, Eric | Analyze the system and ask questions for clarification | Completed
Class Diagram, Enhanced/Original | Leroi | Design class diagram for the original system, added new functions to the enhanced class diagram | Completed
Use Case Diagram | Novia | Examined original use case diagram to determine if changes to it are necissary | Completed
Manual Testing, System 1 program | Eric, Ryan | Tested ui through a number of manual tests | Completed
Improve Pie Charts | Eric | Made the pie charts visually more appealling, made a set list of colors which work well together, moved the amounts off the chart placing them behind the labels instead | Completed
Sort by number division | Ryan | Implement a function that sorts the teacher by division | Completed
Line Charts | Ryan | Added a line chart to display the data | Partially Complete
Assessment of Phase 1 System | Leroi | Reviewed each class, assessing the strengths and weaknesses, wrote up summaries for each class | Complete
Document Improvements to be Implemented | Novia | Created a list of improvents to be implemented | Complete
Timeline | Haris | Created a timeline showing achievements to date, and a concrete plan for achieving stage 2 requirements as well as abstract plan to get from stage 2 to final submission | Complete
Deliverable 2 Matrix | Ryan (did majority), Eric | Matrix showing requirements of current system and test cases involved in testing each requirement | Complete
Test Cases of Required Requirements and Stretch Requirements | Eric, Ryan | Test the requirements that the group implements | Not Started
Save the state | Eric, Stephan, Haris | Save the state of the program | Not Started
Editable Text Fields | Ryan, Stephan | Add a find next, and find prevoius button | Partially Complete
Find all missing Pie charts | Eric | For some embedded elements in the treeview pie charts are not showing up. Find out why and fix it so it renders them | Not Started
Fix naming labels on bar chart | Novia | When the label names are to long it pushes the bar chart out of view. Need to find a way to fix this. Possibly place the words on top of the bars | Not Started
Training Video | Stephan | Create a training video that shows the user how to use the system | Not Started
User Proof Install file | Haris | Create a user proof install file | Not Started